## Sheet1
Task | Start | End | Notes | Phase | Plan
Kick-off & project setup | 2025-10-20 | 2025-10-24 |  | Research & planning
Lit review sprint: scoping & protocol | 2025-10-20 | 2025-11-03 |  | Research & planning
Database search & screening | 2025-11-01 | 2025-11-12 |  | Research & planning
Synthesis write-up (for proposal) | 2025-11-10 | 2025-11-18 |  | Research & planning
Evidence table freeze | 2026-02-07 | 2026-02-07 |  | Evaluation + analysis
Lit update #1 | 2025-11-29 | 2025-11-29
Lit update #2 | 2025-12-20 | 2025-12-20
Lit update #3 | 2026-01-17 | 2026-01-17
Lit update #4 | 2026-02-14 | 2026-02-14
Lit update #5 | 2026-03-14 | 2026-03-14
Refine RQ, Aim & Objectives | 2025-10-20 | 2025-10-26 |  | Research & planning
Project proposal (draft ➜ submit) | 2025-10-20 | 2025-10-27 |  | Research & planning
Progress Log #1 | 2025-10-27 | 2025-10-27 |  | Research & planning
Ethics scoping & route selection | 2025-10-24 | 2025-11-03 |  | Research & planning
DPIA & data security plan | 2025-10-29 | 2025-11-12 |  | Research & planning
Draft consent, PIS, safety-escalation SOP | 2025-10-29 | 2025-11-14 |  | Research & planning
Ethics application prep & submission | 2025-11-05 | 2025-11-21 |  | Research & planning
Define primary/secondary outcomes | 2025-11-05 | 2025-11-12 |  | Research & planning
Power simulation & sample plan | 2025-11-08 | 2025-11-14 |  | Research & planning
Instrumentation & data schema | 2025-11-12 | 2025-11-26 |  | Research & planning
Stat analysis plan + code skeleton | 2025-11-18 | 2025-12-02 |  | Research & planning
NHS content mapping & PIS plain-English check | 2025-11-22 | 2025-11-27 |  | Research & planning
Progress Log #2 | 2025-11-18 | 2025-11-18 |  | Research & planning
System architecture & data model | 2025-11-08 | 2025-11-22 |  | Research & planning
Sprint 1: MVP chat (validation-first) | 2025-11-15 | 2025-12-03 |  | Research & planning
Sprint 2: Memory layer | 2025-12-01 | 2025-12-15 |  | Development (build)
Sprint 3: Safety detection & escalation | 2025-12-05 | 2025-12-20 |  | Development (build)
Sprint 4: Accessibility (TTS/STT, dyslexia-friendly UI) | 2025-12-10 | 2026-01-07 |  | Development (build)
Integration & internal QA | 2026-01-03 | 2026-01-14 |  | Development (build)
Progress Log #3 | 2026-01-07 | 2026-01-07 |  | Development (build)
Pilot recruitment & onboarding | 2026-01-06 | 2026-01-20 |  | Development (build)
Pilot run (2–3 weeks, daily use encouraged) | 2026-01-20 | 2026-02-13
Lightweight interviews (n≈6) for context | 2026-02-10 | 2026-02-17 |  | Evaluation + analysis
Progress Log #4 | 2026-02-12 | 2026-02-12 |  | Evaluation + analysis
Data cleaning & feature engineering | 2026-02-10 | 2026-02-22 |  | Evaluation + analysis
Mixed-effects & bootstrap analysis | 2026-02-16 | 2026-03-08 |  | Evaluation + analysis
Safety metrics (precision/recall) | 2026-02-18 | 2026-03-06 |  | Evaluation + analysis
Usability scale scoring (SUS, UEQ-S) | 2026-03-01 | 2026-03-05 |  | Evaluation + analysis
Rapid qualitative theming & exemplar quotes | 2026-02-24 | 2026-03-06 |  | Evaluation + analysis
Interim report (progress to date) | 2026-02-01 | 2026-02-09 |  | Evaluation + analysis
Write dissertation: Intro & Methods | 2026-02-22 | 2026-03-12 |  | Evaluation + analysis
Write dissertation: Implementation & Results | 2026-03-05 | 2026-03-24 |  | Evaluation + analysis
Write dissertation: Discussion & Conclusions | 2026-03-20 | 2026-03-31 |  | Evaluation + analysis
Edit, figures/tables scripts, appendices | 2026-03-25 | 2026-04-07 |  | Evaluation + analysis
Record viva video (≤20 min) & system demo | 2026-04-05 | 2026-04-12 |  | Write-up & submission
Final checks & submission (all items) | 2026-04-12 | 2026-04-27 |  | Write-up & submission
Supervisor meeting #1 | 2025-10-21 | 2025-10-21 |  | Research & planning
Supervisor meeting #2 | 2025-10-31 | 2025-10-31 |  | Research & planning
Supervisor meeting #3 | 2025-11-14 | 2025-11-14 |  | Research & planning
Supervisor meeting #4 | 2025-11-28 | 2025-11-28 |  | Research & planning
Supervisor meeting #5 | 2025-12-12 | 2025-12-12 |  | Development (build)
Supervisor meeting #6 | 2026-01-09 | 2026-01-09 |  | Development (build)
Supervisor meeting #7 | 2026-01-23 | 2026-01-23 |  | Development (build)
Supervisor meeting #8 | 2026-02-06 | 2026-02-06 |  | Evaluation + analysis
Supervisor meeting #9 | 2026-02-13 | 2026-02-13 |  | Evaluation + analysis
Supervisor meeting #10 | 2026-03-06 | 2026-03-06 |  | Evaluation + analysis
Supervisor meeting #11 | 2026-03-20 | 2026-03-20 |  | Evaluation + analysis
Supervisor meeting #12 | 2026-04-03 | 2026-04-03 |  | Write-up & submission
Supervisor meeting #13 | 2026-04-17 | 2026-04-17 |  | Write-up & submission
Supervisor meeting #14 | 2026-04-24 | 2026-04-24 |  | Write-up & submission
Stakeholder meeting #1 | 2025-11-07 | 2025-11-07 |  | Research & planning
Stakeholder meeting #2 | 2025-12-05 | 2025-12-05 |  | Development (build)
Stakeholder meeting #3 | 2026-01-23 | 2026-01-23 |  | Development (build)
Stakeholder meeting #4 | 2026-03-06 | 2026-03-06 |  | Evaluation + analysis
Usability sessions (clinicians) | 2026-01-20 | 2026-02-13 |  | Development (build)
Lit update — during build | 2025-12-05 | 2025-12-12 |  | Development (build)
Lit update — during write-up | 2026-02-01 | 2026-02-08 |  | Evaluation + analysis
Plan B — IRAS decision & sponsor discussion (conditional) | 2026-05-05 | 2026-05-16 |  | Post-submission (Plan B) | Plan B
Plan B — Draft IRAS pack (protocol, PIS, DPIA, SOP) (conditional) | 2026-05-19 | 2026-06-13 |  | Post-submission (Plan B) | Plan B
Plan B — HRA/REC submission & queries (conditional) | 2026-06-16 | 2026-08-02 |  | Post-submission (Plan B) | Plan B
Plan B — NHS site set-up (Capacity & Capability) (conditional) | 2026-08-05 | 2026-09-12 |  | Post-submission (Plan B) | Plan B
Plan B — Pilot run (service-users) 2–3 weeks (conditional) | 2026-09-15 | 2026-09-30 |  | Post-submission (Plan B) | Plan B